## Sheet1
Risk ID | Category | Description | Probability (1 - 5) | Impact (1 - 5) | Severity | Mitigation
1 | Technical | Hardware or software failures in the production environment | 2 | 4 | 8 | Use reliable hosting providers and maintain backups and redundancy measures
2 | Technical | Images or movie posters are broken | 2 | 3 | 6 | Implement adequate tests and always perform code refactoring when needed
3 | Technical | The database fails to load data | 2 | 5 | 10 | Perform database CRUD functionalities testing
4 | Technical | Checkout page does not display accurate total price | 2 | 5 | 10 | Implement adequate tests and always perform code refactoring when needed
5 | Technical | The application does not meet the requirements set in the MVP | 2 | 5 | 10 | Review completed tasks at the end of each sprint and compare them against the initially set user stories, as well as the client requirements set in the project brief
6 | Complexity | Developing the application could introduce technical challenges that the team is not familiar with | 4 | 4 | 16 | Consult with other team members and/or instructors to ensure a smooth integration of DevOps practices
7 | Security | Data breach compromising customer information | 2 | 5 | 10 | Implement strong security measures, encryption, and regular security audits
8 | Technical | Critical bugs in the booking system | 3 | 4 | 12 | Implement a comprehensive testing strategy, including both unit and integration testing
9 | Competition | The cinema industry is competitive, and the success of the platform depends on effectively standing out in the market | 3 | 4 | 12 | Regularly monitor market, adapt to changes, and differentiate the cinema's offerings
10 | User adoption | Insufficient training and support | 3 | 3 | 9 | Develop user-friendly documentation, provide training sessions for QA cinemas' staff, and offer technical support for customers
11 | Project Management | Inadequate project management and communication | 4 | 3 | 12 | Appoint roles and establish clear communication channels among the development team and stakeholders
12 | Project Management | Inappropriate usage of tools (i.e., linking GitHub issues to tasks on Jira) | 2 | 2 | 4 | Research and understand how to use needed tools